## Project Plan
PROJECT PLAN
| PROJECT TITLE |  | START DATE
| EventCrafters |  | 09-01-2024 |  |  | PROJECT DURATION
| PROJECT MANAGER |  | END DATE |  |  | in days
| Navpreet |  | 30-04-2024 |  |  | #VALUE!
WBS NO. | TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
1 | PROJECT INITIALIZATION | Complete |  | 2024-01-11 | 2024-01-19 | 9 |  | Not Started
1.1 | – Team Charter | Complete | All team members | 2024-02-09 | 2024-02-13 | 5 |  | In Progress
1.1.1 | – Project Charter | Complete | All team members | 2024-02-09 | 2024-02-13 | 5 |  | Complete
1.2 | – Client Letter | Complete | All team members | 2024-02-09 | 2024-02-13 | 5 |  | On Hold
1.3 | – IP Contract Between Client and Team | Complete | All team members | 2024-02-09 | 2024-02-13 | 5
1.4 | – Project Plan | Complete | All team members | 2024-02-09 | 2024-02-13 | 5 |  | ASSIGNMENT
1.5 | – Web Search and Rationale Report | Complete | All team members | 2024-02-09 | 2024-02-13 | 5 |  | JG-Joyekeneth Gamit
1.6 | – Draft PowerPoint Presentation | Complete | All team members | 2024-02-13 | 2024-02-13 | ` |  | DB-Dhwani Bhavsar
2 | Iteration Plans and Agile Backlogs 1 | Complete |  | 2024-02-01 | 2024-02-03 | 3 |  | NN-Navpreet
2.1 | – Rationale | Complete |  | 2024-02-01 | 2024-02-03 | 3
2.2 | – Iteration Plan | Complete |  | 2024-02-01 | 2024-02-03 | 3
2.3 | – Agile Backlog | Complete |  | 2024-02-01 | 2024-02-03 | 3
3 | Iteration Phase 1 & Iteration Plan and Agile Backlog 2 | In Progress |  | 2024-02-13 | 2024-02-18 | 6
3.1 | – 30 percent of the deliverables completed | In Progress |  | 2024-02-13 | 2024-02-18 | 6
3.2 | – Use case diagrams | In Progress |  | 2024-02-13 | 2024-02-18 | 6
3.3 | – Project Updates | In Progress |  | 2024-02-13 | 2024-02-18 | 6
3.3.1 | –– Chart Updates | In Progress |  | 2024-02-13 | 2024-02-18 | 6
4 | Iteration Phase 2 & Iteration Plan and Agile Backlog 3 | Not Started |  | 2024-02-18 | 2024-02-28 | 11
4.1 | – 70 percent of the deliverables are completed | Not Started |  | 2024-02-18 | 2024-02-28 | 11
4.2 | – Use case descriptions that provide a revised list of use case names based on feedback from the Professor/Instructor and/or client | Not Started |  | 2024-02-18 | 2024-02-28 | 11
4.3 | – Project Updates | Not Started |  | 2024-02-18 | 2024-02-28 | 11
5 | Iteration Iteration Components & Iteration Phase 3 | Not Started |  | 2024-03-01 | 2024-03-24 | 24
5.1 | – 100% of all deliverables must be completed | Not Started |  | 2024-03-01 | 2024-03-24 | 24
5.2 | – Finalized use case description names | Not Started |  | 2024-03-01 | 2024-03-24 | 24
5.3 | – incorporate all of the feedback provided in the previous iteration | Not Started |  | 2024-03-01 | 2024-03-24 | 24
5.4 | – Project Updates | Not Started |  | 2024-03-01 | 2024-03-24 | 24