## Iteration 1 Plan
Iteration Plan 2
Project: Event Management
Team Names:EventCrafters
Team Number:04
1. What deliverables did the team plan to complete by the end of the iteration? Refer to your Project Plan submitted in Week 3 to determine which items should be completed. Please note that dates may change as the Iterations continue and various issues arise. Did this Iteration include other work items such as setting up a development environment or bug fixes in the Iteration backlog list?
Number | Description | Responsibility (Initials) | Project Plan adherence?
101 | Discussion of the project topic | DB,JG,NN | Completed
102 | Create Project Plan | DB,JG,NN | Completed
103 | Define Project Scope | DB,JG,NN | Completed
104 | Learn about concept of project | DB,JG,NN | Completed
105 | Research about related websites | DB,JG,NN | Completed
106 | Decide Project name and ideas | DB,JG,NN | Completed
107 | Divided responsibilities | DB,JG,NN | Completed
108 | Decide name of website | DB,JG,NN | Completed
2. Did the team identify the architecture (hardware/software/platform/solution design) early? Was there a architecture owner assigned?
List of architecture being used | Concerns (current and potential) | Owner Assigned (Initials)
Microsoft word | Documentation | JG
Microsoft Excel | Documentation | DB
Google | For research purpose | NN
3. Did your team visually track your progress by using tools such as Microsoft Project, SharePoint, Trello, etc.? Explain why you choose this tool.
Tracking Software Used | Why?
Jira | Ease of use
The point of the Iteration Plan is to have a goal set from the backlog. Iteration Plan and backlog are submitted prior to each iteration. Iteration Plans can repeat work items if feedback is provided by the client that further updates are required for a deliverable. Each iteration should have a working code demostration.
Note: These guiding questions are not meant to be exhaustive. Each team is responsible for the delivery of a workable solution.

## Agile Backlog 1
Iteration 1 Backlog
Notes Iteration 1, all numbers begin with 101 and continue upward. In Iteration 2, all numbers start with 201 and continue upward. In Iteration 3, all numbers begin with 301 and continue upward. Start number column from 101. Outside requirements such as Inception pieces or other requirements are numbered 1-100. PD = Person Day and the number of hours they will spend on a task. Only high-priority items are prioritized, assigned to iteration, and estimated.
Number | Description | PD est. | By
High Priority (light green)
Iteration 1
101 | Project Features | 1 | DB,JG
102 | Learn from similar website for more ideas | 1 | JG
103 | Application's platform | 4 | DB
104 | Scope of project | 1 | DB
105 | Workload division | 3 | DB,JG,NN
106 | Documentation | 8 | NN
107 | Information Collection | 2 | DB,JG,NN
…
Iteration 2
Iteration 3
| Medium Priority (light blue) |  |  | Note: assigned medium and low tasks are prioritized but not yet assigned to iteration, nor estimated.
Low Priority (pink)

## Agile Release Summary 1
Iteration 1: Release Plan Summary
Note The top row lists Number, Feature/Requirement, Inception, Iterations 1, 2, and 3, and Transition. The Number and Feature/Requirements column information is provided in your backlog. The numbers and task must match the backlog information. Once this information is inputted into your release summary chart your team will determine what iteration the tasks will be completed and how many hours are needed to complete each task. Each group should expect to work 9 person-days (PD) per week. A reminder that 1 person day is equal to 4 person hours.
Colour Coding
Inception and Other Requirements (gray) | Iteration 1 (orange) | Iteration 2 (light Blue) | Iteration 3 (light yellow) | Transition (light green)
Number | Feature / Requirement | Inception PD | Iteration #1 PD | Iteration #2 PD | Iteration #3 PD | Transition PD
|  | Due: | Due: | Due: | Due: | Due:
101 | Project Features |  | 14/01/2024
102 | Learn similar website for more concept |  | 17/01/2024
103 | Website's platform |  | 20/01/2024
104 | Scope of project |  | 24/01/2024
105 | Workload division |  | 25/01/2024
106 | Documentation |  | 28/01/2024
107 | Collection of Information |  | 29/01/2024
108 | Implementation of UI |  | 10/02/2024
Work Effort in Person Days (PD) 1 PD hour equals 4 hours |  | 0 | #VALUE! | 0 | 0 | 0
Total Project Hours |  | #VALUE!

## Iteration 2 Plan
Iteration Plan 2
Project
Team Names:Eventcrafters
Team Number:04
1. What deliverables did the team plan to complete by the end of the iteration? Refer to your Project Plan submitted in Week 3 to determine which items should be completed. Please note that dates may change as the Iterations continue and various issues arise. Did this Iteration include other work items such as setting up a development environment or bug fixes in the Iteration backlog list?
Number | Description | Responsibility (Initials) | Project Plan adherence?
201 | Create beginning of the website | DB,JG | Completed
202 | Research about theme and images | NN | Completed
203 | Work on inception phase | DB,JG,NN | Completed
204 | Create all diagrams in Iteration phase 1 | DB,JG | Completed
205 | Continuosly test and optimize performance of website | JG | Completed
206 | Backend:User Registration and login | DB | Completed
207 | Backend:User Authentication | DB | Completed
2. Did the team identify the architecture (hardware/software/platform/solution design) early? Was there a architecture owner assigned?
List of architecture being used | Concerns (current and potential) | Owner Assigned (Initials)
Reactjs | To develop wesite | DB
Firebase | For saving data | DB
XML | For application layout | JG
Visual studio | For coding | DB
Visual paradigm | Create diagrams | DB,JG
Microsoft word | To create documents | NN
Microsoft Excel | To store and make project work plan | JG
3. Is your team still using the tracking software for your project? Are there any significant timeline changes to your project?
Tracking Software | Progress & Updates
Git | To upload and store project
The point of the Iteration Plan is to have a goal set from the backlog. Iteration Plan and backlog are submitted prior to each iteration. Iteration Plans can repeat work items if feedback is provided by the client that further updates are required for a deliverable. Each iteration should have a working code demostration.
Note: These guiding questions are not meant to be exhaustive. Each team is responsible for the delivery of a workable solution.

## Agile Backlog 2
Iteration 2 Backlog
Notes Iteration 1, all numbers begin with 101 and continue upward. In Iteration 2, all numbers start with 201 and continue upward. In Iteration 3, all numbers begin with 301 and continue upward. Start number column from 201. Outside requirements such as Inception pieces or other requirements are numbered 1-100. PD = Person Day and the number of hours they will spend on a task. Only high-priority items are prioritized, assigned to iteration, and estimated.
Number | Description | PD est. | By
High Priority
Iteration 1
101 | Project Features | 1 | DB,JG
102 | Learn from similar website for more ideas | 1 | JG
103 | Application's platform | 4 | DB
104 | Scope of project | 1 | DB
105 | Workload division | 3 | DB,JG,NN
106 | Documentation | 8 | NN
107 | Information Collection | 2 | DB,JG,NN
Iteration 2
201 | Create Home page of the websites | 5 | DB,JG
202 | Research data and images | 2 | NN
203 | Work on inception phase | 8 | DB,JG,NN
204 | Create all diagrams | 4 | DB,JG
205 | Continuosly test and optimize performance of website | 2 | JG
206 | Work on Backend:User Registration and login | 3 | DB
207 | Create Event Page | 2 | DB,JG
Iteration 3
Medium Priority
Low Priority

## Agile Release Summary 2
Iteration 2: Release Plan Summary
Note The top row lists Number, Feature/Requirement, Inception, Iterations 1, 2, and 3, and Transition. The Number and Feature/Requirements column information is provided in your backlog. The numbers and tasks must match the backlog information. Once this information is inputted into your release summary chart your team will determine what iteration the tasks will be completed and how many hours are needed to complete each task. Each group should expect to work 9 person-days (PD) per week. A reminder that 1 person day is equal to 4 person hours.
Colour Coding
Inception and Other Requirements (gray) | Iteration 1 (orange) | Iteration 2 (light Blue) | Iteration 3 (light yellow) | Transition (light green)
Number | Feature / Requirement | Inception | Iteration #1 | Iteration #2 | Iteration #3 | Transition
|  | Due: | Due: | Due: | Due: | Due:
101 | Project Features |  | 14/01/2024
102 | Learn similar website for more concept |  | 17/01/2024
103 | Website's platform |  | 20/01/2024
104 | Scope of project |  | 24/01/2024
105 | Workload division |  | 25/01/2024
106 | Documentation |  | 28/01/2024
107 | Collection of Information |  | 29/01/2024
108 | Implementation of UI |  | 10/02/2024
201 | Create beginning of the website |  |  | 13/02/2024
202 | Research about theme and images |  |  | 13/02/2024
203 | Work on inception phase |  |  | 14/02/2024
204 | Create all diagrams in Iteration phase 1 |  |  | 17/02/2024
205 | Continuosly test and optimize performance of website |  |  | 18/02/2024
206 | Backend:User Registration and login |  |  | 19/02/2024
207 | Backend:User Authentication |  |  | 19/02/2024
Work Effort in Person Days (PD) 1 PD hour equals 4 hours |  | 0 | #VALUE! | #VALUE! | 0 | 0
Total Project Hours |  | #VALUE!

## Iteration 3 Plan
Iteration Plan 3
Project
Team Names:
Team Number:
1. What deliverables did the team plan to complete by the end of the iteration? Refer to your Project Plan submitted in Week 3 to determine which items should be completed. Please note that dates may change as the Iterations continue and various issues arise. Did this Iteration include other work items such as setting up a development environment or bug fixes in the Iteration backlog list?
Number | Description | Responsibility (Initials) | Project Plan adherence?
2. Did the team identify the architecture (hardware/software/platform/solution design) early? Was there a architecture owner assigned?
List of architecture being used | Concerns (current and potential) | Owner Assigned (Initials)
3. Is your team still using the tracking software for your project? Are there any significant timeline changes to your project?
Tracking Software | Progress & Updates
The point of the Iteration Plan is to have a goal set from the backlog. Iteration Plan and backlog are submitted prior to each iteration. Iteration Plans can repeat work items if feedback is provided by the client that further updates are required for a deliverable. Each iteration should have a working code demostration.
Note: These guiding questions are not meant to be exhaustive. Each team is responsible for the delivery of a workable solution.

## Agile Backlog 3
Iteration 3 Backlog
Notes Iteration 1, all numbers begin with 101 and continue upward. In Iteration 2, all numbers start with 201 and continue upward. In Iteration 3, all numbers begin with 301 and continue upward. Start number column from 201. Outside requirements such as Inception pieces or other requirements are numbered 1-100. PD = Person Day and the number of hours they will spend on a task. Only high-priority items are prioritized, assigned to iteration, and estimated.
Number | Description | PD est. | By
High Priority
Iteration 1
Iteration 2
Iteration 3
Medium Priority
Low Priority

## Agile Release Summary 3
Iteration 3: Release Plan Summary
Note The top row lists Number, Feature/Requirement, Inception, Iterations 1, 2, and 3, and Transition. The Number and Feature/Requirements column information is provided in your backlog. The numbers and task must match the backlog information. Once this information is inputted into your release summary chart your team will determine what iteration the tasks will be completed and how many hours are needed to complete each task. Each group should expect to work 9 person-days (PD) per week. A reminder that 1 person day is equal to 4 person hours.
Colour Coding
Inception and Other Requirements (gray) | Iteration 1 (orange) | Iteration 2 (light Blue) | Iteration 3 (light yellow) | Transition (light green)
Number | Feature / Requirement | Inception | Iteration #1 | Iteration #2 | Iteration #3 | Transition
|  | Due: | Due: | Due: | Due: | Due:
Work Effort in Person Days (PD) 1 PD hour equals 4 hours |  | 0 | 0 | 0 | 0 | 0
Total Project Hours |  | 0